## Sheet1
Project plan	Date	Description
Initial project plan	27-Oct	Describe the project's general aims, objectives, and scope at this phase. I use this plan as the basis for everything I do after that.
Preparation of PDM plan	28-Oct	Draft a Project Development Management (PDM) plan that outlines the project's schedule, duties, and responsibilities. This guarantees that I carry out and oversee my work in an organised manner.
Presentation of PDM plan	29-Oct	Develop and provide a presentation outlining my PDM plan to stakeholders throughout this step. My objective is to convey the project's objectives, schedule, and resource needs in an effective manner.
Research and Data preprocessing	30-Oct	I will collect pertinent literature and datasets for the study throughout this phase, making care to properly clean and prepare the data. To make sure I get high-quality input data for model training, this step is essential.
Model development	31-Oct	I will develeop the model which is efficient way for the classification.
Data ethics preparation	01-Nov	Preparation for Data ethics quiz
Data ethics quiz	02-Nov	Quiz day
Model evaluation	03-Nov	Analysing the model with performance and accuracy which meets the project goal.
Full implimentation	04-Nov	full implementation
Report creation	05-Nov	Report will be created for project
Preparation for VIVA	06-Nov	Prepare and attend the mock VIVA.
Report Submission	07-Nov	Report submission day
Viva	10-Jan	Attend the Viva to showcase my work.